## Parts List External
ITEM | DESCRIPTION | QTY | MATERIAL -SPECIFICATIONS | PART NUMBER | FROM WHERE | READY TO ORDER? | DATE EXPECTED | STATUS | HAVE IT? | ANY PROBLEMS | IDENTICAL?
4 | JGY-370Output Shaft | 2 |  |  | COMMUNICA |  |  |  | X |  | X
14 | JGY-37012V DC Motor | 2 |  |  | COMMUNICA |  |  |  | X |  | X
21 | JGY-370Gearbox | 2 |  |  | COMMUNICA |  |  |  | X |  | X
1 | M5-washer | 28 |  |  | HARDWARE STORE | X |  |  |  |  | X
6 | 6mm D SHAFT | 4 | STEEL | M001 | HARDWARE STORE |  | 2023-08-04 | ordered |  |  | X
7 | Tail | 1 |  |  | HARDWARE STORE |  |  |  | X |  | X
9 | 5m hex nut | 12 |  |  | HARDWARE STORE |  |  |  | X |  | X
11 | M5 BOLT FLATTENED | 4 | STEEL | M002 | HARDWARE STORE |  | 2023-08-04 | ordered |  |  | X
16 | m5-bolt-long | 3 |  |  | HARDWARE STORE |  |  |  | X |  | X
17 | m3 bolt | 8 |  |  | HARDWARE STORE |  |  |  | X |  | X
18 | M5-nut-4mm | 3 |  |  | HARDWARE STORE |  |  |  | X |  | X
22 | M3-nut | 12 |  |  | HARDWARE STORE |  |  |  | X |  | X
23 | m3 bolt long | 12 |  |  | HARDWARE STORE |  |  |  | X |  | X
2 | SHAFT EXTENSION | 2 | STEEL | M003 | Micro robotics |  | 2023-08-04 | ordered coupling |  |  | X
3 | Sun gear | 4 | ACRYLIC |  | NETRAM |  | 2023-08-04 | ordered |  |  | X
5 | Idler Gear | 8 | ACRYLIC |  | NETRAM |  | 2023-08-04 | ordered |  |  | X
8 | tail fin | 4 | MDF |  | NETRAM |  | 2023-08-04 | ordered |  |  | X
10 | Spur Gear22 | 8 | ACRYLIC |  | NETRAM |  | 2023-08-04 | ordered |  |  | X
12 | Wheel | 4 | MDF |  | NETRAM |  | 2023-08-04 | ordered |  |  | X
13 | bottom plate | 2 | MDF |  | NETRAM |  | 2023-08-04 | ordered |  |  | X
15 | side plate | 2 | MDF |  | NETRAM |  | 2023-08-04 | ordered |  |  | X
19 | Back Plate | 1 | MDF |  | NETRAM |  | 2023-08-04 | ordered |  |  | X
20 | front plate | 1 | MDF |  | NETRAM |  | 2023-08-04 | ordered |  |  | X
24 | Frame | 4 | ACRYLIC |  | NETRAM |  | 2023-08-04 | ordered |  |  | X
25 | Standoff-thin | 24 | ACRYLIC |  | NETRAM |  | 2023-08-04 | ordered |  |  | X
26 | Standoff-thick | 12 | ACRYLIC |  | NETRAM |  | 2023-08-04 | ordered |  |  | X

## Parts List University
ITEM | DESCRIPTION | QTY | MATERIAL -SPECIFICATIONS | PART NUMBER | FROM WHERE | READY TO ORDER? | STATUS | HAVE IT? | ANY PROBLEMS | IDENTICAL?
4 | JGY-370Output Shaft | 2 |  |  | COMMUNICA | X |  |  |  | X
14 | JGY-37012V DC Motor | 2 |  |  | COMMUNICA | X |  |  |  | X
21 | JGY-370Gearbox | 2 |  |  | COMMUNICA | X |  |  |  | X
1 | M5-washer | 28 |  |  | HARDWARE STORE |  |  | X |  | X
7 | Tail | 1 |  |  | HARDWARE STORE |  |  | X |  | X
9 | 5m hex nut | 12 |  |  | HARDWARE STORE |  |  | X |  | X
16 | m5-bolt-long | 3 |  |  | HARDWARE STORE |  |  | X |  | X
17 | m3 bolt | 8 |  |  | HARDWARE STORE |  |  | X |  | X
18 | M5-nut-4mm | 3 |  |  | HARDWARE STORE |  |  | X |  | X
22 | M3-nut | 12 |  |  | HARDWARE STORE |  |  | X |  | X
23 | m3 bolt long | 12 |  |  | HARDWARE STORE |  |  | X |  | X
3 | Sun gear | 4 | ACRYLIC |  | UNIVERSITY LASER CUT |  | purchasing material |  |  | X
5 | Idler Gear | 8 | ACRYLIC |  | UNIVERSITY LASER CUT |  | purchasing material |  |  | X
8 | tail fin | 4 | MDF |  | UNIVERSITY LASER CUT | X |  |  |  | X
10 | Spur Gear22 | 8 | ACRYLIC |  | UNIVERSITY LASER CUT |  | purchasing material |  |  | X
12 | Wheel | 4 | MDF |  | UNIVERSITY LASER CUT | X |  |  |  | X
13 | bottom plate | 2 | MDF |  | UNIVERSITY LASER CUT | X |  |  |  | X
15 | side plate | 2 | MDF |  | UNIVERSITY LASER CUT | X |  |  |  | X
19 | Back Plate | 1 | MDF |  | UNIVERSITY LASER CUT | X |  |  |  | X
20 | front plate | 1 | MDF |  | UNIVERSITY LASER CUT | X |  |  |  | X
24 | Frame | 4 | ACRYLIC |  | UNIVERSITY LASER CUT |  | purchasing material |  |  | X
25 | Standoff-thin | 24 | ACRYLIC |  | UNIVERSITY LASER CUT |  | purchasing material |  |  | X
26 | Standoff-thick | 12 | ACRYLIC |  | UNIVERSITY LASER CUT |  | purchasing material |  |  | X
2 | SHAFT EXTENSION | 2 | STEEL | M003 | UNIVERSITY MMW |  | in queue |  |  | X
6 | 6mm D SHAFT | 4 | STEEL | M001 | UNIVERSITY MMW |  | in queue |  |  | X
11 | M5 BOLT FLATTENED | 4 | STEEL | M002 | UNIVERSITY MMW |  | in queue |  |  | X